# SmartRPD Web Beta Scope and Detailed Work Breakdown Structure

Target beta release for user testing by end of July 2026

| Field | Value |
| --- | --- |
| Document ID | SmartRPD-WEB-BETA-SCOPE-WBS |
| Version | 1.0 |
| Date | 2026-05-01 |
| Owner | Shaikh Faid |

# 1. Purpose and Beta Objective

The objective is to restructure the SmartRPD Web into a beta-delivery plan that can guide development, testing, and stakeholder review. The beta target is end of July 2026, where selected users can use and test SmartRPD Web with the core viewer, manual 2D design, synchronized case data, improved registration, and initial server-side DLL integration.

This revision removes or defers items that are not required for the July beta and breaks each relevant web-app area into actionable tasks with dependencies and acceptance criteria.

# 2. Beta Scope Summary

| Workstream | Beta Outcome | Priority |
| --- | --- | --- |
| 3D Object Rendering | Users can open a case and reliably view required jaw/STL/derived SmartRPD artifacts in the browser with consistent controls and visual states. | Must Have |
| 2D Design Manual Editing - Web | Users can manually create, edit, remove, and review removable partial denture components through a practical web UI. | Must Have |
| API Saving and Loading Sync | Web app can save and load design/viewer data/annotations through APIs using the same database records as SmartRPD desktop. | Must Have |
| 3D Viewer UI/UX Revamp and Loading Optimization | Viewer page is easier to use, gives clear loading/progress states, and handles large files with less waiting and fewer page freezes. | Must Have |
| 2D Design Logic - SmartRPD Desktop C# | Desktop app can read, validate, and write the same 2D component data model used by the web app. | Must Have |
| User Registration and Sign Up | New users can register from the web app through a simplified, validated registration flow. | Should Have |
| DLL Function Integration | Required DLL functions can be invoked from the web workflow through a controlled server-side service or API layer. | Must Have for selected functions |

# 3. Assumptions and Constraints

The July 2026 beta is for controlled user testing, not a full production release.

The web client remains based on the existing Three.js viewer and current SmartRPD Web structure unless a specific feature requires refactoring.

DLL functions are executed server-side. The browser does not run native Windows DLLs directly.

Database consistency between SmartRPD Web and SmartRPD desktop is a core acceptance requirement.

Any workflow that affects clinical or design output requires verification against sample cases before beta testing.

# 3. Detailed Work Breakdown Structure

## 5.1 3D Object Rendering

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 3D-01 | Audit current viewer pipeline | Review STL/OFF loading, camera controls, model orientation, object grouping, visibility toggles, and current failure cases. | Existing ThreeDViewer page and loaders | Known issues and supported artifact types are documented before implementation starts. |
| 3D-02 | Standardize renderable artifact model | Define how jaw models, generated surfaces, polylines, polyline points, gingival curve, buccal curve, undercut visuals, playdoh and artificial tooth meshes are represented in web memory. | API data contract | Each artifact has type, case ID, source, visibility state, and transform/orientation metadata. |
| 3D-03 | Jaw/STL rendering reliability | Improve loading and rendering for upper/lower jaw STL files, including missing file handling and consistent orientation. | Existing STL loader | Sample cases open without blank viewer states or incorrect initial camera framing. |
| 3D-04 | Render generated surfaces and meshes | Load and render generated RPD surfaces or derived mesh outputs from the database. | API loading | Generated artifacts appear with correct material, opacity, and visibility controls. |
| 3D-05 | Render polylines, gingival curves, buccal curves | Render design guide curves, boundaries, selected points, and other non-mesh geometry. | Data schema for curve/point artifacts | Curves can be shown/hidden and remain aligned to the jaw model. |
| 3D-06 | Viewer state persistence | Persist camera, selected jaw, visible layers, opacity, and display mode where required. | Default to web code | Reopening a case restores the expected viewer state for the workflow. |
| 3D-07 | Rendering QA sample set | Prepare representative cases for large, small, upper/lower, partial, and error-state models. | Sample data | QA checklist confirms rendering consistency across sample cases. |

## 5.2 2D Design Manual Editing - Web UI

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 2D-WEB-01 | Define component list | Confirm removable partial denture components supported for, such as clasp, rest, major connector, minor connector, denture base, mesh, guide plane | Clinical/design input | Supported and deferred components are explicitly listed. |
| 2D-WEB-02 | Define component data model | Use existing common structure for component type, jaw, tooth, material, notes, and validation flags. | Desktop C# sync model | Web and desktop use equivalent fields and versioning. |
| 2D-WEB-03 | Component creation tools | Implement tools to place supported components on the 2D design tooth template | New 2D Design editing page | User can add each component type to a case. |
| 2D-WEB-04 | Manual edit operations | Support select, add, delete, modify, and cancel/undo, reset for manual editing. | Component creation tools | User can correct mistakes without restarting the design. |
| 2D-WEB-05 | Component properties panel | Provide UI for material, side and all supported components for each material | Component data model | Property edits update the design and are saved through API. |
| 2D-WEB-06 | Validation and constraints | Add basic rules for required fields, invalid empty paths, unsupported material/component combinations, and incomplete design warnings. | Component rules | Invalid design states are visible before saving. |
| 2D-WEB-07 | History and version handling | Track edits during a session and update-current-version as agreed. | API version contract | Reloading the case shows the correct saved version. |
| 2D-WEB-08 | 2D design usability QA | Test common editing flows using real sample cases and collect user pain points. | test manual editing | Core edit operations are documented and pass the test checklist. |

## 5.3 API Saving and Loading Sync

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| API-01 | Map existing SmartRPD database records | Identify current tables/collections/files used by SmartRPD desktop and the web app for cases, users, STL files, design data, and generated artifacts. | Database access and desktop schema knowledge | Mapping document identifies source of truth for every data item. |
| API-02 | Define shared API contract | Specify API endpoints for load case, save 2D design, load 2D design, save DLL job outputs, and load generated artifacts. | Data model | API request/response examples are documented. |
| API-03 | Implement save 2D design endpoint | Persist component JSON and metadata in the database with case ID, user ID, version, timestamps, and compatibility flags. | Auth/session handling. Reuse of existing implementation. | Saved design can be reloaded by web and desktop. |
| API-04 | Implement load 2D design endpoint | Return 2D design with all component data needed by web UI and desktop C#. | Save endpoint | Web editor can reconstruct all saved components. |
| API-05 | Data consistency checks | Add validation for case ownership, schema mismatches. | API contract | Conflicting or invalid saves return clear errors. |
| API-06 | Regression tests and API examples | Create Postman/API test cases for save/load and cross-app consistency. | Endpoint implementation | Test set can be run before each build. |

## 5.4 3D Viewer UI/UX Revamp and Loading Optimization

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| UX-01 | Viewer workflow review | Review current page flow from case selection to viewer load, controls, design entry, and error recovery. | Existing UI | Priority UX issues are listed and assigned. |
| UX-02 | Revamp viewer layout | Reorganize toolbar, object/layer list, camera controls, material controls, and action buttons, navigation tab | 3D jaw model | Controls are discoverable and do not block the model view. |
| UX-03 | Loading and progress states | Show clear progress for model download, parsing, rendering, API calls, and DLL job polling. | API/client integration | Users can tell what is happening during long operations. |
| UX-04 | Large file optimization | Reduce initial blocking work, defer non-critical layers, clean up old objects/materials, and avoid repeated downloads where possible. | Viewer pipeline audit | Large sample cases load with fewer freezes and lower memory growth. |
| UX-05 | Error and empty states | Handle missing STL, failed API call, failed DLL job, invalid data, and unsupported browser cases with clear recovery options. | API error codes | No workflow fails silently. |
| UX-06 | Responsive and browser checks | Verify supported desktop & mobile browser sizes and minimum laptop resolutions for testing. | Updated UI | Controls remain usable on agreed devices. |

## 5.5 2D Design Logic - SmartRPD Desktop C#

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 2D-CS-01 | Review desktop design model | Identify current C# classes, serialization, validation, and database access related to RPD design components. | Desktop source access | Desktop model gaps against web data model are documented. |
| 2D-CS-02 | Implement shared component classes | Add or update C# classes to match the web 2D component schema. | Component data model | Desktop can deserialize web-saved designs without data loss. |
| 2D-CS-03 | Desktop load support | Load web-saved 2D design data into SmartRPD desktop and map to existing desktop objects or display structures vice-versa. | API/database contract | A design saved on web appears correctly on desktop. |
| 2D-CS-04 | Desktop save/write-back support | Save desktop edits in the same structure expected by the web app vice-versa. | Shared classes | A design edited on desktop reloads correctly on web. |
| 2D-CS-05 | Validation parity | Implement matching rules for required fields, component/material combinations, and incomplete design states. | Web validation rules | Web and desktop reject or warn on the same invalid cases. |
| 2D-CS-06 | Cross-app consistency test | Run web-to-desktop-to-web and desktop-to-web-to-desktop round trips on sample cases. | Implemented load/save | Round-trip tests show no lost components, shifted coordinates, or material mismatches. |

## 5.6 User Registration and Sign Up

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| REG-01 | Review current registration flow | Document why the current new-user process is troublesome, including required manual steps and data fields. | Current auth/user process | Pain points and required fields are confirmed. |
| REG-02 | Define registration requirements | Confirm fields such as username, email, role, password, otp | Stakeholder input | Approved registration field list exists. |
| REG-03 | Create web registration page | Implement sign-up page with validation, password rules, duplicate email handling, and success/failure states. | Auth API | New user can submit registration from the web app. |
| REG-04 | Registration API integration | Connect sign-up page to backend user creation or approval workflow. | Backend/user DB | Submitted user appears in the correct user store with expected status. |
| REG-05 | Login handoff and messaging | After registration, guide user to login, pending approval, or email verification depending on agreed flow. | Registration requirements | User sees clear next step after sign-up. |
| REG-06 | Security checks | Validate password handling, server-side validation, duplicate prevention, and access restrictions before account approval. | Auth implementation | No client-only validation is relied upon for account creation. |

## 5.7 DLL Function Integration

| ID | Task | Description | Dependencies | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| DLL-01 | Confirm DLL function list | Identify exactly which DLL functions are needed | Clinical/design workflow priority | Approved DLL function list exists. |
| DLL-02 | Define invocation architecture | Decide server-side wrapper approach, hosting OS, input/output file paths, job IDs, timeouts, and logging. | DLL technical constraints | Architecture supports reliable invocation without browser-native DLL execution. |
| DLL-03 | Create wrapper/service layer | Implement controlled service to call DLL functions with validated inputs and structured outputs. | Invocation architecture | Service can run selected DLL function on a test case. |
| DLL-04 | Async job handling | Add job submission, status polling, cancellation/failure handling, retries where safe, and result retrieval. | API job contract | Web UI can submit and monitor long-running DLL tasks. |
| DLL-05 | Persist DLL outputs | Save generated artifacts and metadata using the same API/database structure used by the viewer. | API artifact endpoints | DLL result can be re-opened in web and desktop where applicable. |
| DLL-06 | Error handling and logs | Capture DLL errors, invalid inputs, missing files, timeout failures, and crash cases for support. | Wrapper/service layer | Failures return clear UI messages and useful logs. |

# 6. Milestone Plan Toward End-July Beta

| Milestone | Target Window | Key Outputs |
| --- | --- | --- |
| M1 - Scope Lock and Data Contract | Week 1, June 2026 | Finalize component list, API/data model, DLL function list, and sample cases. |
| M2 - Core Save/Load and Viewer Foundation | Weeks 2-3, June 2026 | Implement API save/load skeleton, artifact discovery, reliable STL loading, and viewer loading states. |
| M3 - 2D Web Editor and Desktop Classes Parity | Weeks 3-5, June to early July 2026 | Manual component creation/editing, shared data model, desktop C# load/save support. |
| M4 - DLL Integration and Generated Artifact Rendering | Weeks 5-6, July 2026 | Server-side DLL wrapper, job flow, persisted outputs, and rendered generated artifacts. |
| M5 - Registration, UX Polish, and Optimization | Weeks 6-7, July 2026 | Registration page, viewer layout revamp, loading optimization, error states. |
| M6 - Beta Stabilization and User Test Readiness | Final week of July 2026 | Regression tests, round-trip consistency checks, test guide, known issues list, release candidate build. |

# 7. Beta Acceptance Criteria

A beta user can register or be onboarded through the improved web registration flow.

A beta user can open an assigned case and load the required 3D jaw model without manual file handling.

The 3D viewer shows clear loading, error, layer, and material/visibility states.

A beta user can create and edit the agreed manual 2D RPD components on the web app.

The web app can save and reload 2D design data through APIs.

SmartRPD desktop C# can load the same saved 2D design data and preserve consistency on write-back.

Selected DLL functions can run through a server-side integration and return outputs usable by the web app.

A sample case can complete the agreed beta flow from load, edit, save, desktop consistency check, generated output, and reload.

# 8. Key Risks and Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Database schema mismatch between web and desktop | Saved designs may not round-trip correctly. | Lock shared schema early and test web-desktop-web round trips weekly. |
| DLL functions require Windows-only runtime or special dependencies | Deployment complexity and beta delay. | Confirm runtime in Week 1 and isolate DLL execution in a dedicated worker/service. |
| Large STL or generated meshes slow down the browser | Poor beta user experience. | Optimize loading, defer layers, add progress states, and test large sample cases early. |
| 2D component scope grows beyond July capacity | Beta misses target or ships unstable editing. | Freeze beta component list and defer non-critical components after July. |
| Registration requirements are unclear | Sign-up page may not match operational process. | Confirm exact approval, verification, and required fields before implementation. |
| Generated artifact formats are inconsistent | Viewer cannot render outputs reliably. | Standardize artifact metadata and write import adapters per artifact type. |